## Project Data
Project Name | AIlixir Intelligence
Online team meeting | https://tu-berlin.zoom-x.de/j/68161739941?pwd=Tz3duoAQeQHGWAsBNMexRqNxlnSPCI.1
Production system (if any) | ...
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2026ss03-ailixir-intelligence
GitHub feature board | https://github.com/orgs/amosproj/projects/99
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/103/views/1
Position of T-shirt logo | Upper Torso Center Large
Link to logo for black T-shirt | ...
Link to logo for white T-shirt | ...
Additional materials | ...
Team maling list | oss-amos-proj3@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Brüggemann | Jonas | jonasbrue | jonas.brueggemann@campus.tu-berlin.de
Khan | Muhamad | mukahn | md.kahn@tu-berlin.de
Ebied | Andrew | andrewluka | a.ebied@campus.tu-berlin.de
Vinzens | Hannes | hannes-v | hannes.vinzens@fau.de
Ahmed | Hasnat | hasnatahmed331 | hasnat.ahmed@fau.de
Busse | Tobias | aseuc | tobias.t.busse@fau.de
Sandt | Eloi | eloinoel | eloi.sandt@campus.tu-berlin.de
Amer | Hossam | Hossam-Amer | hossam.amer@fau.de
Zeeshan | Muhamad | MuhammadZeeshan2 | sharif.zeeshan@fau.de
Haseeb | Abdul | AbdulHaseeb-SE | abdul.ah.haseeb@fau.de
Vogt | Marcel | VogtIndustries | marcel.vogt@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2026-04-15 |  | Eloi | Everyone else | N/A | COACH student
2 | 2026-04-22 | Eloi | Tobias | Everyone else | Muhamad Khan | COACH student
3 | 2026-04-29 | Tobias | Eloi | Everyone else | Andrew Ebied | COACH student
4 | 2026-05-06 | Eloi | Jane | Everyone else | Hannes Vinzens | COACH student
5 | 2026-05-13 | Jane | Eloi | Everyone else | Hasnat Ahmed | COACH student
6 | 2026-05-20 | Eloi | Tobias | ... | Hossam Amer | COACH student
7 | 2026-05-27 | Tobias | Eloi |  | Muhamad Zeeshan | COACH student
8 | 2026-06-03 | Eloi | Tobias |  | Abdul Haseeb | COACH student
9 | 2026-06-10 | Tobias | Eloi |  | Marcel Vogt | COACH student
10 | 2026-06-17 | Eloi | Tobias |  | Muhamad Khan | COACH student
11 | 2026-06-24 | Tobias | Eloi |  | Andrew Ebied | COACH student
12 | 2026-07-01 | Eloi | Tobias |  | Hannes Vinzens | COACH student
13 | 2026-07-08 | Tobias | Eloi |  | Hasnat Ahmed | COACH student
14 | 2026-07-15 | Eloi | / |  | Hossam Amer | COACH student | Demo day!
15 | 2026-07-22 |  | / |  |  | COACH student | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Deliver MVP
mutual and personal improvement
deliver a maintainable prototype that can be potentially used as a starting point for the industry partner
Meeting norms | Meeting Should stick to deliverables.
maybe once or twice per week. for each meeting, a document should be made that includes the points which we will go over. the document could be edited by anyone in case anyone has points they want to discuss in the meeting, although this might be particularly useful for POs.
write an email in case you will be late/unable to attend team meetings
be on time
mute yourself in calls if you don't talk
Protocol industry partner meetings
Team Meeting starts at 12 (30 minutes earlier)
Working norms
deciding on a release manager should be part of the team meetings
Would be cool if we could give an estimate of when we will be available to work, and if possible, also specify on which issues and till when we expect to be finished with them. in case of delays, i think they should be communicated as well so that the team gets a rough idea of when they could be done or if help is needed from other people
SDs can self-assign issues at will; if that doesn't work out, issues will be assigned during team meetings
Coding (style) guidelines, common AI agent setup, CI/CD linting/formating checks
Documentation (how to run + code comments)
Testing the written code/feature. All tests should pass before merging to main/master
git flow strategy for working on code
Definition of Done (DoD) A checklist of criteria (e.g. tests passed, code reviewed, documentation updated) that must be met before an issue is considered finished
Definition of Ready (DoR); whether or not devs have enough capacity to take on an issue and finish it in time
Pull Requests need to be reviewed and approved by at least one other developer
Coordination norms
Bigger decisions will be put to vote (ideally on slack)
Work should be distributed with clear boundaries.
use feature board actively and communicate with other people to coordinate work
Communication norms
replies within ~24h
would also be cool if people communicate if they are unable to reply within 24h, with an estimate of when they will reply
Communication with the industry partner over Slack
it would also be nice to have dedicated communication channels for the team internally and with the industry partner. another dedicated channel for SDs as well
agree on one main channel of communication: Slack
Respect, active listening, tolerance
Consideration norms
Respect, Communicate Conflicts
be kind and be cooperative
Cont. improvement norms | constructive criticism
open feedback about things that could be improved
Rewards
eat ice cream together at the end of the course
Sanctions
gets brought up in the meeting
Signatures
Scrum Master | Jonas Brüggemann
Product owner | Eloi Sandt
Product owner | Tobias Busse
Software developer | Hasnat Ahmed
Software developer | Hossam Amer
Software developer | Hannes Vinzens
Software developer | Muhammad Zeeshan
Software developer | Abdul Haseeb
Software developer | Andrew Ebied
Software developer | Marcel Vogt

## Product Goal
Product Vision | Project Mission
The reason of existence of the envisioned product (beyond this project). | The reason of existence of the envisioned product (beyond this project).

## Product Glossary
Term | Definition

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Optional
5 | Write your sprint goal here
6
7
8
9
10
11
12
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment

## Planning Poker
Last Name | First Name | Value
Brüggemann | Jonas | 0 | 0 | OK
Khan | Muhamad | 0
Ebied | Andrew
Vinzens | Hannes
Ahmed | Hasnat |  | 0 | No size
#REF! | #REF! |  | 1 | Trivial size
Sandt | Eloi |  | 2 | Small size
Busse | Tobias |  | 3 | Medium size
Zeeshan | Muhamad |  | 5 | Large size
Haseeb | Abdul |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value