## Project Data
Project Name | AIlixir Intelligence
Online team meeting | https://tu-berlin.zoom-x.de/j/68161739941?pwd=Tz3duoAQeQHGWAsBNMexRqNxlnSPCI.1
Production system (if any) | ...
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2026ss03-ailixir-intelligence
GitHub feature board | https://github.com/orgs/amosproj/projects/99
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/103/views/1
Position of T-shirt logo | Upper Torso Right Small
Link to logo for black T-shirt | https://www.shirtinator.com/s/w1QJzfDfTC-gGBjVmnCscg
Link to logo for white T-shirt | https://www.shirtinator.com/s/sMNil0MoQzmuNuc04Y6Ljw
Additional materials | https://join.slack.com/t/ailixirintelligence/shared_invite/zt-41vmwcfed-bx98eWnpC0NWgsF~CCTlLw
Team maling list | oss-amos-proj3@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Brüggemann | Jonas | jonasbrue | jonas.brueggemann@campus.tu-berlin.de
Ebied | Andrew | andrewluka | a.ebied@campus.tu-berlin.de
Vinzens | Hannes | hannes-v | hannes.vinzens@fau.de
Ahmed | Hasnat | hasnatahmed331 | hasnat.ahmed@fau.de
Busse | Tobias | aseuc | tobias.t.busse@fau.de
Sandt | Eloi | eloinoel | eloi.sandt@campus.tu-berlin.de
Amer | Hossam | Hossam-Amer | hossam.amer@fau.de
Zeeshan | Muhamad | MuhammadZeeshan2 | sharif.zeeshan@fau.de
Haseeb | Abdul | AbdulHaseeb-SE | abdul.ah.haseeb@fau.de
Vogt | Marcel | VogtIndustries | marcel.vogt@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2026-04-15 |  | Eloi | Everyone else | N/A | COACH student
2 | 2026-04-22 | Eloi | Tobias | Everyone else | Andrew Ebied | COACH student
3 | 2026-04-29 | Tobias | Eloi | Everyone else | Andrew Ebied | COACH student
4 | 2026-05-06 | Eloi | Tobias | Everyone else | Hasnat Ahmed | COACH student
5 | 2026-05-13 | Tobias | Eloi | Everyone else | Hossam Amer | COACH student
6 | 2026-05-20 | Eloi | Tobias | ... | Muhamad Zeeshan | COACH student
7 | 2026-05-27 | Tobias | Eloi |  | Hannes Vinzens | COACH student
8 | 2026-06-03 | Eloi | Tobias |  | Marcel Vogt | COACH student
9 | 2026-06-10 | Tobias | Eloi |  | Abdul Haseeb | COACH student
10 | 2026-06-17 | Eloi | Tobias |  | Hannes Vinzens | COACH student
11 | 2026-06-24 | Tobias | Eloi |  | Hasnat Ahmed | COACH student
12 | 2026-07-01 | Eloi | Tobias |  | Hossam Amer | COACH student
13 | 2026-07-08 | Tobias | Eloi |  | Muhamad Zeeshan | COACH student
14 | 2026-07-15 | Eloi | / |  | Abdul Haseeb | COACH student | Demo day!
15 | 2026-07-22 |  | / |  |  | COACH student | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Deliver MVP
mutual and personal improvement
deliver a maintainable prototype that can be potentially used as a starting point for the industry partner
Meeting norms | Meeting Should stick to deliverables.
maybe once or twice per week. for each meeting, a document should be made that includes the points which we will go over. the document could be edited by anyone in case anyone has points they want to discuss in the meeting, although this might be particularly useful for POs.
write an email in case you will be late/unable to attend team meetings
be on time
mute yourself in calls if you don't talk
Protocol industry partner meetings
Team Meeting starts at 12 (30 minutes earlier)
Working norms
deciding on a release manager should be part of the team meetings
Would be cool if we could give an estimate of when we will be available to work, and if possible, also specify on which issues and till when we expect to be finished with them. in case of delays, i think they should be communicated as well so that the team gets a rough idea of when they could be done or if help is needed from other people
SDs can self-assign issues at will; if that doesn't work out, issues will be assigned during team meetings
Coding (style) guidelines, common AI agent setup, CI/CD linting/formating checks
Documentation (how to run + code comments)
Testing the written code/feature. All tests should pass before merging to main/master
git flow strategy for working on code
Definition of Done (DoD) A checklist of criteria (e.g. tests passed, code reviewed, documentation updated) that must be met before an issue is considered finished
Definition of Ready (DoR); whether or not devs have enough capacity to take on an issue and finish it in time
Pull Requests need to be reviewed and approved by at least one other developer
Coordination norms
Bigger decisions will be put to vote (ideally on slack)
Work should be distributed with clear boundaries.
use feature board actively and communicate with other people to coordinate work
Communication norms
replies within ~24h
would also be cool if people communicate if they are unable to reply within 24h, with an estimate of when they will reply
Communication with the industry partner over Slack
it would also be nice to have dedicated communication channels for the team internally and with the industry partner. another dedicated channel for SDs as well
agree on one main channel of communication: Slack
Respect, active listening, tolerance
Consideration norms
Respect, Communicate Conflicts
be kind and be cooperative
Cont. improvement norms | constructive criticism
open feedback about things that could be improved
Rewards
eat ice cream together at the end of the course
Sanctions
gets brought up in the meeting
Signatures
Scrum Master | Jonas Brüggemann
Product owner | Eloi Sandt
Product owner | Tobias Busse
Software developer | Hasnat Ahmed
Software developer | Hossam Amer
Software developer | Hannes Vinzens
Software developer | Muhammad Zeeshan
Software developer | Abdul Haseeb
Software developer | Andrew Ebied
Software developer | Marcel Vogt

## Product Goal
Product Vision | Project Mission
AIlixir Intelligence transforms unstructured documents into connected, actionable knowledge. Users can upload or scan documents (e.g., medical reports, invoices), from which the system extracts domain-specific, meaningful data fields and organises them into a personalised knowledge base. An AI-powered voice/chat interface enables users to ask precise, context-aware questions and better understand their personal documents, as well as relationships and developments across their document history. At its core, the platform is designed to be domain-agnostic and configurable for a wide range of use cases. | The mission of this project is to create an MVP that runs on mobile devices. Core functionality includes extracting structured information from uploaded documents, storing and organising it within a personal knowledge base, and enabling conversational querying using RAG with optional enrichment from external knowledge sources such as research papers. The system will demonstrate domain configurability using medical documents as the primary domain and finance as a secondary domain.

## Product Glossary
Term | Definition
AiLixir | A mobile application that lets users capture or upload documents, extract structured knowledge from them, and ask an AI questions about the analysed content.
User | A person who uses AiLixir to manage documents, start knowledge extraction, view results, and interact with the AI.
Account | A user identity that stores private app data and enables access to personalised documents, chats, and extracted knowledge.
Registration / Sign-up | The process by which a new user creates an account, typically using email, password, and required personal details.
Login | The process by which an existing user proves their identity and gains access to private app screens and backend functionality.
Authenticated User | A user who has successfully logged in and is allowed to access private documents, protected screens, and authenticated backend APIs.
Document | A user-provided file or scan that can be stored, previewed, analysed, and used as the source for knowledge extraction.
Captured Document | A document created by taking a picture or scan with the smartphone camera and passing the result back to the app.
Uploaded Document | A document selected from the device file system or submitted from the camera that becomes available inside AiLixir.
Document Preview | A small visual representation of a selected document or document page before the user starts analysis or extraction.
Document View | The screen that lists the documents stored for the authenticated user and acts as the entry point to document actions.
Document Details View | The screen for one document that displays metadata, pages, status, and actions such as starting extraction or downloading results.
Document Metadata | Descriptive information about a document, such as status, size, filename, document date, upload date, facility, and tags.
Document Page | An individual page or image belonging to a document, especially relevant for multi-page uploads or camera scans.
Document Tag / Label | A user-facing classification attached to a document, for example a lab result label, used to organize and filter documents.
Document Status | The current processing state of a document, such as not extracted, extraction in progress, or analysed.
Knowledge Extraction | The user-triggered process that converts document content into structured domain information, such as entities and relationships.
Extraction Status | An indicator showing whether knowledge has already been extracted from a document, is still being extracted, or has not been extracted yet.
Medical Document | A document containing medical information, such as a lab report, discharge summary, diagnosis information, medication information, or blood marker data.
Blood Biomarker | A measurable health value extracted from medical documents and displayed over time in the medical dashboard.
Medical Dashboard | A visual overview that shows extracted medical data, including biomarkers, historical trends, and filterable health information.
Financial Metric | A financial value extracted from documents or connected sources, such as balances, asset values, transaction data, or portfolio performance data.
Finance Dashboard | A visual overview that consolidates financial metrics and transactions and presents portfolio performance over time.
Structured Data | A machine-readable representation of extracted information, typically JSON or graph data, that downstream services can process reliably.
Domain-specific Entity | A meaningful object identified in a document, such as Patient, Diagnosis, Medication, MedicalReport, or a financial transaction.
Relationship | A typed connection between two domain-specific entities, such as HAS_DIAGNOSIS, PRESCRIBED_FOR, MENTIONS_DIAGNOSIS, or TREATED_BY.
Triple | A structured fact consisting of a subject entity, a relationship, and an object entity, prepared for knowledge graph ingestion.
Knowledge Graph | A structured network of entities and relationships extracted from documents and used to support retrieval, validation, visualisation, and LLM answers.
Node | An entity stored in the knowledge graph, such as a patient, diagnosis, medication, or document.
Edge | A relationship stored in the knowledge graph that connects two nodes and expresses how they are related.
Graph Database | Persistent storage for knowledge graph nodes and edges, implemented either as a dedicated graph database or another schema that can store triples.
Graph Ingestion | The act of writing extracted nodes and edges into the knowledge graph database so that they can be retrieved later.
Subgraph | A relevant subset of the knowledge graph returned for a specific query or prompt, usually consisting of targeted nodes and their direct edges.
Graph Retrieval | The process of finding and returning a query-relevant subgraph so that another service, especially the LLM integration, can use it as context.
LLM | A language model that generates answers for users and can use retrieved graph data as grounding context.
AI Agent | The conversational assistant in the app that receives user prompts and returns answers about uploaded and analysed documents.
Prompt | A user input to the AI agent, typed or spoken, that asks for information or analysis about uploaded and analysed documents.
LLM Context | Structured information provided to the LLM before answer generation so that answers can reference verified extracted facts.
JSON Context Window | A JSON-formatted representation of graph facts that is injected into the LLM prompt for initial integration and validation.
Hallucination | An AI answer that is not supported by verified extracted facts; the knowledge graph is intended to reduce this risk.
GraphRAG Framework | A framework-based approach for extracting, storing, and retrieving graph-based knowledge for use with generative AI.
Manual JSON Pipeline | An extraction approach in which entities and relationships are first produced as structured JSON before being sent to an ingestion service.
Embedding | A vector representation of data sources such as PDFs, images, JSON files, or knowledge graphs, used for retrieval in a RAG setup.
RAG Database | A retrieval database that stores embeddings and supports finding relevant information for AI-generated answers.
Knowledge Graph Visualisation | A visual representation of a document's extracted graph, typically as a node-link diagram or structured report.
Knowledge Graph PDF Export | A generated PDF representation of a document's knowledge graph that the user can download and inspect locally.
Chat Screen | The app screen that displays user prompts and AI-agent responses and provides input controls for text and voice interaction.
Voice Dictation | A microphone-based input mode that turns spoken language into a text prompt for the AI agent.
Voice Conversation | A voice-based interaction mode in which the user can converse with the AI agent without relying only on typed prompts.
Backend API | A service interface that allows the frontend to authenticate users, store and retrieve documents, trigger extraction, and request generated results.
Document API | Backend functionality that accepts document uploads, returns the user's stored documents, and retrieves a document by document ID.
Persistent App Storage | Long-term storage for user accounts, chats, document identifiers, document metadata, and document files.
OCR | The process of converting text from scanned or photographed documents into machine-readable text before downstream extraction.
ElevenLabs Agent | An external voice agent service used for AI voice conversations.
Voice Call | A mode where users can speak with the AI and receive audio responses.

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Refine the knowledge graph pipeline, set up the database for persistent app storage, and implement a consistent layout.
5 | Implement user authentication and backend integration for document uploads while building the frontend UI components and backend pipeline required for knowledge graph extraction.
6 | Complete the end-to-end application by integrating frontend views with backend APIs, enabling knowledge graph extraction and providing visualisation options for extracted knowledge graphs.
7 | Improve knowledge graph quality, introduce AI chat capabilities, and enhance the user experience with document handling and usability improvements.
8 | Create a unified user knowledge graph and connect it to the chat system, enabling context-aware conversations and persistent chat management.
9 | Enable an AI chat assistant experience through Knowledge Graph improvements, chat integration, and voice/camera capabilities.
10 | Establish the foundation for a research-aware voice AI assistant that can understand spoken input, respond with synthesized speech, and provide research-backed answers.
11 | Implement a hybrid context strategy for AI chat by combining Knowledge Graph and research paper retrieval, while improving answer transparency through source attribution and and further developing the voice chat capabilities.
12 | Complete the research-aware AI assistant by integrating the full research knowledge base into contextual retrieval, providing transparent source-backed responses, and finalising end-to-end voice conversations.
13 | Complete any remaining feature work from previous sprints, finalize the voice AI assistant, and prepare the project for handover with testing, code cleanup, and comprehensive documentation.
14
15

## Velocity Tracking
Sprint # | Story Points Realized | Average
1 |  | 26.2727
2 | 23 | 26.2727
3 | 18 | 26.2727
4 | 13 | 26.2727
5 | 37 | 26.2727
6 | 26 | 26.2727
7 | 18 | 26.2727
8 | 39 | 26.2727
9 | 33 | 26.2727
10 | 21 | 26.2727
11 | 17 | 26.2727
12 | 44 | 26.2727
13 |  | 26.2727
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 121 | 121
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 | Establish the project foundation by completing initial research, defining the app direction, and setting up the frontend development environment. |  | 0 | 121 | 0 | 121
2 | Deliver the first functional application prototype with document upload, authentication UI, architecture planning, and initial document analysis capabilities. |  | 24 | 121 | 23 | 121
3 | Build the core document management UI, define the app navigation structure, and implement document capture using the camera while establishing the backend cloud infrastructure. |  | 18 | 97 | 18 | 98
4 | Refine the knowledge graph pipeline, set up the database for persistent app storage, and implement a consistent layout. |  | 18 | 79 | 13 | 80
5 | Implement user authentication and backend integration for document uploads while building the frontend UI components and backend pipeline required for knowledge graph extraction. |  | 29 | 61 | 37 | 67
6 | Complete the end-to-end application by integrating frontend views with backend APIs, enabling knowledge graph extraction and providing visualisation options for extracted knowledge graphs. |  | 32 | 32 | 26 | 30
Features
1 | Establish the project foundation by completing initial research, defining the app direction, and setting up the frontend development environment. | Setup documentation README.md
Research which extraction tool do we use? (Document AI, OCR, OCR with Google AI)
App Design Mockups / Wireframes / Moodboard
Frontend Setup Development Environment for App
2 | Deliver the first functional application prototype with document upload, authentication UI, architecture planning, and initial document analysis capabilities. | Implement Document Analysis and Structured Data Output (JSON) | 8 |  | 8
|  | Deliverable: Software Architecture Design | 8 |  | 8
|  | Frontend: Github Actions CI/CD Pipeline | 3 |  | 3
|  | Interface includes a document upload screen | 3 |  | 2
|  | App Login Screen | 2 |  | 2
3 | Build the core document management UI, define the app navigation structure, and implement document capture using the camera while establishing the backend cloud infrastructure. | Frontend: Documents Overview | 3 |  | 5
|  | Capturing Documents using Camera/Scanning | 5 |  | 3
|  | App Navigation Tree | 5 |  | 5
|  | Setup GCP | 5 |  | 5
4 | Refine the knowledge graph pipeline, set up the database for persistent app storage, and implement a consistent layout. | Knowledge Graph Pipeline Refinement | 8 |  | 5
|  | Set up Database for App Persistent Storage | 5 |  | 5
|  | Consistent Layout | 5 |  | 3
5 | Implement user authentication and backend integration for document uploads while building the frontend UI components and backend pipeline required for knowledge graph extraction. | User Registration (Sign Up) View | 1 |  | 1
|  | User Registration (Functionality) | 3 |  | 2
|  | Login Authentication Process | 5 |  | 5
|  | Knowledge Graph Download Button | 2 |  | 3
|  | UI for Knowledge Extraction | 2 |  | 2
|  | Extracting Knowledge Graphs from Documents | 8 |  | 13
|  | Backend API: Documents | 5 |  | 8
|  | GCP Scheduling Extraction | 3 |  | 3
6 | Complete the end-to-end application by integrating frontend views with backend APIs, enabling knowledge graph extraction and providing visualisation options for extracted knowledge graphs. | Connecting Document Views to Backend | 5 |  | 3
|  | Connect Knowledge Extraction UI to Backend | 5 |  | 3
|  | Connecting Document Upload to Backend | 3 |  | 5
|  | Home Screen with Appropriate Navigation Options | 3 |  | 5
|  | Simple Combining Knowledge Graphs | 8 |  | 5
|  | Backend Deployment: Knowledge Graph Components | 8 |  | 5
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 264 | 264
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
7 | Improve knowledge graph quality, introduce AI chat capabilities, and enhance the user experience with document handling and usability improvements. |  | 31 | 264 | 33 | 264
8 | Create a unified user knowledge graph and connect it to the chat system, enabling context-aware conversations and persistent chat management. |  | 45 | 233 | 47 | 231
9 | Enable an AI chat assistant experience through Knowledge Graph improvements, chat integration, and voice/camera capabilities. |  | 39 | 188 | 38 | 184
10 | Establish the foundation for a research-aware voice AI assistant that can understand spoken input, respond with synthesized speech, and provide research-backed answers. |  | 35 | 149 | 32 | 146
11 | Implement a hybrid context strategy for AI chat by combining Knowledge Graph and research paper retrieval, while improving answer transparency through source attribution and and further developing the voice chat capabilities. |  | 44 | 114 | 41 | 114
12 | Complete the research-aware AI assistant by integrating the full research knowledge base into contextual retrieval, providing transparent source-backed responses, and finalising end-to-end voice conversations. |  | 47 | 70 | 44 | 73
13 | Complete any remaining feature work from previous sprints, finalize the voice AI assistant, and prepare the project for handover with testing, code cleanup, and comprehensive documentation. |  | 23 | 23 | 0 | 29
Features
7 | Improve knowledge graph quality, introduce AI chat capabilities, and enhance the user experience with document handling and usability improvements. | Fix: Knowledge Graph Extraction API | 3 |  | 3 | not completed
|  | Knowledge Graph Refinement | 5 |  | 5
|  | API: LLM Chat Agent | 5 |  | 5 | not completed
|  | Chat Screen | 5 |  | 5
|  | Deleting Documents | 3 |  | 5
|  | Fix: Account Signup | 3 |  | 3
|  | Preview of Uploaded Documents | 2 |  | 2 | not completed
|  | Componentisation - Technical Debt - Beautify | 5 |  | 5 | not completed
8 | Create a unified user knowledge graph and connect it to the chat system, enabling context-aware conversations and persistent chat management.
|  | API: LLM Chat Agent | 5 |  | 5
|  | Fix: Knowledge Graph Extration API | 3 |  | 5
|  | Knowledge Graph Context into LLM Prompts | 8 |  | 8 | not completed
|  | Deploy user knowledge graph in backend | 3 |  | 5
|  | Creating Chats | 1 |  | 3
|  | Persistent Chat History | 5 |  | 3
|  | Preview of Uploaded Documents | 2 |  | 2
|  | Chat Overview | 3 |  | 1
|  | Chat Database | 5 |  | 5
|  | Componentisation - Technical Debt - Beautify | 5 |  | 5
|  | Combining all document sub-graphs into one | 5 |  | 5
9 | Enable an AI chat assistant experience through Knowledge Graph improvements, chat integration, and voice/camera capabilities. | Fix: Retrieving the Knowledge Graph | 2 |  | 2 | not completed
|  | Chat Agent Uses History | 3 |  | 3
|  | Knowledge Graph Context into LLM Prompts | 8 |  | 8
|  | Deployment of Knowledge Graph Context Chat on Backend | 5 |  | 8
|  | Update Neo4j / GCP License for Knowledge Extraction | 1 |  | not completed
|  | Connect Chat Screen with LLM Chat Agent | 3 |  | 3 | not completed
|  | Dictate Chat Function | 8 |  | 5
|  | Integrate Camera Scanning | 5 |  | 5
|  | Deleting Chats | 3 |  | 3
|  | Password show/hide button | 1 |  | 1
10 | Establish the foundation for a research-aware voice AI assistant that can understand spoken input, respond with synthesized speech, and provide research-backed answers. | Scraping Research Papers | 8 |  | 8
|  | Fix: Retrieving the Knowledge Graph | 2 |  | 2
|  | Rate Limiting on document upload | 3 |  | not completed
|  | Deploy Neo4j Graph Database | 5 |  | 5
|  | Fix: Authentication | 3 |  | 3
|  | Connect Chat Screen with LLM Chat Agent | 3 |  | 3
|  | AI Voice Call using Elevenlabs | 8 |  | 8 | not completed
|  | Voice Call Indicator | 3 |  | 3 | not completed
11 | Implement a hybrid context strategy for AI chat by combining Knowledge Graph and research paper retrieval, while improving answer transparency through source attribution and and further developing the voice chat capabilities. | Knowledge Graph Context + Research Paper RAG Hybrid LLM Approach | 8 |  | 8 | not completed
|  | Custom LLM API for Elevenlabs Voice Chat Agents | 8 |  | 5
|  | Downloading all Research Papers | 5 |  | 5 | not completed
|  | Chat Naming function | 5 |  | 5
|  | Add Chat Message Thinking States | 2 |  | 2
|  | Voice Call Indicator | 3 |  | 3 | not completed
|  | AI Voice Call using ElevenLabs | 8 |  | 8 | not completed
|  | Expo Build Pipeline | 5 |  | 5
12 | Complete the research-aware AI assistant by integrating the full research knowledge base into contextual retrieval, providing transparent source-backed responses, and finalising end-to-end voice conversations. | Sources for an LLM Answer | removed |  | /
|  | Ensure Knowledge Graph Correctness | removed |  | /
|  | Knowledge Graph Context + Research Paper RAG Hybrid LLM Approach | 8 |  | 8
|  | Integrate full Research Paper Knowledge Base into RAG contextualisation | 8 |  | 8
|  | Downloading all Research Papers | 5 |  | 8
|  | Knowledge Graph Visualisation Instructions Wiki | 2 |  | 2
|  | Setup Elevenlabs Agent in IP project | 3 |  | not completed
|  | AI Voice Call using ElevenLabs | 8 |  | 13
|  | Connect Voice Call Mode with App UI | 2 |  | 2
|  | Formatting of chat messages | 3 |  | 3
|  | Voice Call Indicator | 3 |  | not completed
|  | Voice Call Transcription | 5 |  | not completed
|  | Displaying sources in LLM answers | removed |  | /
13 | Complete any remaining feature work from previous sprints, finalize the voice AI assistant, and prepare the project for handover with testing, code cleanup, and comprehensive documentation. | Voice Call Transcription | removed
|  | Voice Call Indicator | removed
|  | Ensure Knowledge Graph Correctness | removed
|  | Update Documentation + Architecture Description | deliverable |  | /
|  | Update Dependencies List | deliverable |  | /
|  | Code Cleanup + Code Documentation | 5
|  | Update ReadMe | 3
|  | Make backend robust to vector DB not being available | 2
|  | Add names of papers used to the llm reply metadata | 3
|  | Submit Chat message via "Enter" | 1
|  | Make Upload Page Scrollable | 1
|  | Fix 'delete' swipe gesture in Chats page | 1
|  | Duplicate Add Page / Camera Button | 1
|  | Remove Microphone Button (Dictate) | 1
|  | Remove "Download graph" Button | 1
|  | Make Document Detail Narrative Scrollable | 1
|  | Fix Logout button | 1
|  | Make font bigger | 1
|  | Remove STT Testpage button | 1
|  | PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB |  |  |  | When a backlog item says "not completed", and is worked on in a later sprint, the est. size will be mirrored in real size to not distort the burndown chart with duplicates in the next sprint. The real "real size" of an item can be found in the sprint it was completed in.

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
| The feature code has been reviewed and approved by at least one team member (e.g. pull request approved). | The project builds, deploys, runs, and tests successfully in a clean environment (CI/CD pipeline passes). | Application passes (user) testing across Android and iOS mobile devices.
| The feature code is merged into the main branch without breaking other functionality. | Sprint release notes are written, summarising the modifications made during the sprint. | User documentation is updated to provide instructions on how to build and use the application.
| The feature was manually tested and works as expected without critical bugs. |  | Design documentation is updated to reflect the architecture and system design.
Feature components are demo-ready.

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment
| firebase:functions | @elevenlabs/elevenlabs-js | ^2.53.0 | MIT
| firebase:functions | firebase-admin | ^13.6.0 | Apache 2.0
| firebase:functions | firebase-functions | ^7.0.0 | MIT
| poc/elevenlabs-token-service | @hono/node-server | ^1.19.14 | MIT
| poc/elevenlabs-token-service | firebase-admin | ^14.0.0 | Apache-2.0
| poc/elevenlabs-token-service | hono | ^4.12.25 | MIT
| poc/elevenlabs-token-service | @elevenlabs/elevenlabs-js | 2.52.0 | MIT
| frontend | react-native-community/cli | latest | MIT
| frontend | react-native-markdown-display | ^7.0.2 | MIT
| frontend | pdf-lib | ^1.17.1 | MIT
| frontend | livekit-client | 2.16.0 | Apache-2.0
| frontend | firebase | ^12.13.0 | Apache-2.0
| frontend | expo-sharing | ~55.0.19 | MIT
| frontend | expo-file-system | ~55.0.21 | MIT
| frontend | expo-dev-client | 55.0.35 | MIT
| frontend | expo-asset | ~55.0.17 | MIT
| frontend | axios | ^1.16.1 | MIT
| frontend | react-native-async-storage/async-storage | 2.2.0 | MIT
| frontend | react-native-webrtc | ^137.0.2 | MIT
| frontend | livekit/react-native-expo-plugin | ^1.0.2 | Apache-2.0
| frontend | livekit/react-native | 2.9.4 | Apache-2.0
| frontend | expo-google-fonts/raleway | ^0.4.2 | MIT
| frontend | expo-audio | ~55.0.14 | MIT
| frontend | elevenlabs/react-native | ^1.2.11 | MIT
| frontend | @langchain/react | ^1.0.17 | MIT
| frontend | @langchain/core | ^1.1.48 | MIT
| frontend | @assistant-ui/react-native | ^0.1.21 | MIT
| frontend | @assistant-ui/react-langchain | ^0.0.12 | MIT
| frontend | @assistant-ui/react | ^0.14.14 | MIT
| frontend | @react-navigation/bottom-tabs | ^7.15.5 | MIT
| frontend | @react-navigation/elements | ^2.9.10 | MIT
| frontend | @react-navigation/native | ^7.1.33 | MIT
| frontend | @tamagui/config | ^2.0.0-rc.41 | MIT
| frontend | @tamagui/lucide-icons-2 | ^2.0.0-rc.41 | MIT
| frontend | expo | ~55.0.15 | MIT
| frontend | expo-constants | ~55.0.14 | MIT
| frontend | expo-device | ~55.0.15 | MIT
| frontend | expo-document-picker | ~55.0.13 | MIT
| frontend | expo-font | ~55.0.6 | MIT
| frontend | expo-glass-effect | ~55.0.10 | MIT
| frontend | expo-image | ~55.0.8 | MIT
| frontend | expo-image-picker | ~55.0.20 | MIT
| frontend | expo-linking | ~55.0.13 | MIT
| frontend | expo-router | ~55.0.12 | MIT
| frontend | expo-splash-screen | ~55.0.18 | MIT
| frontend | expo-status-bar | ~55.0.5 | MIT
| frontend | expo-symbols | ~55.0.7 | MIT
| frontend | expo-system-ui | ~55.0.15 | MIT
| frontend | expo-web-browser | ~55.0.14 | MIT
| frontend | react | 19.2.0 | MIT
| frontend | react-dom | 19.2.0 | MIT
| frontend | react-hook-form | ^7.73.1 | MIT
| frontend | react-native | 0.83.4 | MIT
| frontend | react-native-gesture-handler | ~2.30.0 | MIT
| frontend | react-native-reanimated | 4.2.1 | MIT
| frontend | react-native-safe-area-context | ~5.6.2 | MIT
| frontend | react-native-screens | ~4.23.0 | MIT
| frontend | react-native-svg | 15.15.3 | MIT
| frontend | react-native-web | ~0.21.0 | MIT
| frontend | react-native-worklets | 0.7.2 | MIT
| frontend | tamagui | ^2.0.0-rc.41 | MIT
| frontend | @types/react | ~19.2.2 | MIT
| frontend | eslint | ^9.0.0 | MIT
| frontend | eslint-config-expo | ~55.0.0 | MIT
| frontend | eslint-config-prettier | ^10.1.8 | MIT
| frontend | eslint-config-universe | ^15.0.3 | MIT
| frontend | eslint-plugin-prettier | ^5.5.5 | MIT
| frontend | prettier | ^3.8.3 | MIT
| frontend | typescript | ~5.9.2 | Apache-2.0
| frontend | jotai | ^2.20.0 | MIT
| frontend | @tanstack/query | ^5.100.9 | MIT
| frontend | expo-linear-gradient | ~55.0.14 | MIT
| frontend | expo-clipboard | ~55.0.13 | MIT
| frontend | @react-three/drei | ^10.7.7 | MIT
| frontend | @react-three/fiber | ^9.6.1 | MIT
| frontend | @types/three | ^0.184.1 | MIT
| frontend | expo-gl | ~55.0.14 | MIT
| frontend | three | ^0.184.0 | MIT
| backend | neo4j | 6.1.0 | Apache 2.0 AND Python-2.0
| backend | numpy | 2.2.6 | BSD License
| backend | openai | 2.34.0 | Apache Software License
| backend | opencv-python | 4.12.0.88 | Apache Software License
| backend | paddleocr | 3.5.0 | Apache License 2.0
| backend | pandas | 3.0.2 | BSD License
| backend | pillow | 12.2.0 | MIT-CMU
| backend | pydantic | 2.13.3 | MIT
| backend | python-dotenv | 1.2.2 | BSD-3-Clause
| backend | requests | 2.33.1 | Apache Software License
| backend | protobuf | 3.20.2 | BSD-3-Clause
| backend | fast-api | 0.136.1 | MIT
| backend | uvicorn | 0.46.0 | BSD-3-Clause
| backend | firebase-admin | 7.4.0 | Apache-2.0
| backend | google-cloud-firestore | 2.27.0 | Apache-2.0
| backend | python-multipart | 0.0.27 | Apache-2.0

## Planning Poker
Last Name | First Name | Value
Brüggemann | Jonas | 0 | 0 | OK
Khan | Muhamad | 0
Ebied | Andrew
Vinzens | Hannes
Ahmed | Hasnat |  | 0 | No size
Amer | Hossam |  | 1 | Trivial size
Sandt | Eloi |  | 2 | Small size
Busse | Tobias |  | 3 | Medium size
Zeeshan | Muhamad |  | 5 | Large size
Haseeb | Abdul |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value